## Sheet1
I) | Group number: | 2
II) | The number of weeks planned to complete a project: | 9 | weeks
S.NO.: | Project Perfomance Measure | Values | Comments
| BAC= | 300000
| PV= | 150000
| EV= | 135000
| AC= | 172500
1 | CPI= | 0.78261 | 0.78 is less than 1.0, that means it is over planned cost
2 | SPI= | 0.45 | 0.45 is less than 1.0 that means it is behind schedule
3 | EAC= | 641018.5185
4 | Percentage | 213.6728 | %
5 | TCPI= | 1.2941 | 0.29 additional budget hours required to reach EAC
| New BAC | 330000
| New TCPI= | 1.2381 | 0.24 additional budget hours required to reach EAC
1.24 < 1.29. So, it will be easier to complete the project.