## Title
Course
OM&IS 690
Project Name
Husky Air Database Management
Group Name
2
Submitted By
Nitish Katkoori (Z1942695)
Srikanth Reddy Narra (Z1947038)
Tianyu Nan (Z1831431)
Date
2022-07-17

## Work Breakdown Structure
WBS Level | WBS Code | WBS Name | WBS Description | Person Responsible | Duration (Days) | Start | End
1 | 1 | Analysis Phase | Analyses all the requirements for development and the project | Nitish Katkoori | 23 | 2022-05-14 | 2022-06-06
2 | 1.1 | Requirement Gathering and analysis | Project Manager to collect all the needed requirements from customer and Husky Air for development of the project | Nitish Katkoori | 1 | 2022-05-14 | 2022-05-15
2 | 1.2 | Stakeholder Interviews | Project manager schedules interview with stakeholder on clarifications required by the team | Nitish Katkoori | 2 | 2022-05-15 | 2022-05-17
2 | 1.3 | Create requirements document | Project manager collect all of the requirements and produce a document for requirements | Nitish Katkoori | 5 | 2022-05-19 | 2022-05-26
3 | 1.3.1 | Business Case | Produce the reason and primary goal for this project | Nitish Katkoori | 1 | 2022-05-19 | 2022-05-20
3 | 1.3.2 | Create project charter | Produce project charter document | Nitish Katkoori | 2 | 2022-05-21 | 2022-05-23
3 | 1.3.3 | Project Scope | Produce the needs and things that are required to be determined for this project | Nitish Katkoori | 2 | 2022-05-24 | 2022-05-26
2 | 1.4 | Project Schedule | Project manager creates tasks and assigning deadlines for development, testing and deployment of the project by considering the efforts required | Nitish Katkoori | 10 | 2022-05-26 | 2022-06-05
1 | 2 | Application Designing | Design the application for mobile devices and website | Project Team | 3 | 2022-06-06 | 2022-06-09
2 | 2.1 | Software and Hardware requirements | Project team analyses all the requirements for software and hardware | Project Team | 3 | 2022-06-06 | 2022-06-09
1 | 3 | Webpage Design | Frontend team write HTML code for webpage design | Tianyu Nan | 28 | 2022-06-09 | 2022-07-07
2 | 3.1 | Home page and login page for Website | Frontend development team creates high level design for website | Tianyu Nan | 2 | 2022-06-09 | 2022-06-11
3 | 3.1.1 | User Interface design for Mobile application | Frontend development team works on developing customer login screen to the mobile application | Tianyu Nan | 4 | 2022-06-11 | 2022-06-15
3 | 3.1.2 | User Interface design for Web application | The UI for customer login to the web based application is developed by frontend team | Tianyu Nan | 5 | 2022-06-15 | 2022-06-20
2 | 3.2 | User aggrement/ policy page | Design user aggrement or policy page for both Website and mobile application | Tianyu Nan | 1 | 2022-06-20 | 2022-06-21
3 | 3.2.1 | Agreement/ policy page design for Mobile application | Frontend team design a screen for agreement/ policies for mobile application based on page resolution upon login | Tianyu Nan | 1 | 2022-06-21 | 2022-06-22
3 | 3.2.2 | Agreement/ Policy page design for Web application | Frontend team design a screen for agreement/ policies for Web application based on page resolution | Tianyu Nan | 1 | 2022-06-22 | 2022-06-23
2 | 3.3 | Visual design for Website and mobile application | Frontend team develops design for website and mobile application with all dropdown actions | Tianyu Nan | 6 | 2022-06-23 | 2022-06-29
3 | 3.3.1 | Design page for Menu Dropdown | Frontend team devlop a menu drop down with Pilot availability,available aircrafts, customer request interface and scheduling interface | Tianyu Nan | 7 | 2022-06-29 | 2022-07-06
1 | 4 | Backend Code Development | Software development including coding, database implementation and security | Tianyu Nan | 60 | 2022-07-07 | 2022-09-05
2 | 4.1 | Login page credentials validation | Backend team develops a code to validate the login credentials with the data maintained in database | Tianyu Nan | 25 | 2022-07-08 | 2022-08-02
2 | 4.2 | Data base code for Menu Dropdown | Technical team write the backend code to show the following information in application drop downs | Tianyu Nan | 12 | 2022-08-03 | 2022-08-15
3 | 4.2.1 | Pilot availability | This code shows the pilots availability and is only accessible by Husky Air | Tianyu Nan | 8 | 2022-08-16 | 2022-08-24
3 | 4.2.2 | Available aircraft models | The customers can choose the available aircraft models based on their luggage | Tianyu Nan | 3 | 2022-08-25 | 2022-08-28
3 | 4.2.3 | Customer Requests interface | The customer requests for travel are put pool for approval by Husky air | Tianyu Nan | 3 | 2022-08-29 | 2022-09-01
3 | 4.2.4 | Scheduling interface | Pilot assignment based on customer requests of Husky air | Tianyu Nan | 4 | 2022-09-01 | 2022-09-05
1 | 5 | System Interfacing | Technical team to Integrate frontend page with backend logic | Tianyu Nan | 22 | 2022-09-06 | 2022-09-28
2 | 5.1 | Login page | Interface login page with backend logic credential validation code | Tianyu Nan | 5 | 2022-09-15 | 2022-09-20
2 | 5.2 | Menu Dropdown | Interface Menu dropdow page with corresponding backend logic | Tianyu Nan | 8 | 2022-09-20 | 2022-09-28
1 | 6 | Data maintenance and migration | Technical team updates the previous data of Husky air and the new transactional data to uskay air Database | Tianyu Nan | 13 | 2022-10-02 | 2022-10-15
2 | 6.1 | Data Migration | Technical team transports all the data from the pervious spreadsheet to new system database | Tianyu Nan | 9 | 2022-10-02 | 2022-10-11
2 | 6.2 | Store login details for patients and pilots | Store all the web/ application login and passwords details of pilots and patients to only allow access for registered users | Tianyu Nan | 2 | 2022-10-11 | 2022-10-13
1 | 7 | Quality Analysis/ Testing | Testing team prepare test cases and the results are documented | Srikanth Reddy Narra | 22 | 2022-10-15 | 2022-11-06
2 | 7.1 | Create test cases | Create the possible test cases to find any deviations from the usual process of application | Srikanth Reddy Narra | 2 | 2022-10-15 | 2022-10-17
2 | 7.2 | Validate test cases | Test the application for originality by testing team | Srikanth Reddy Narra | 5 | 2022-10-17 | 2022-10-22
2 | 7.3 | Document results | Testing team to document the results obtained while testing and revert to development team, if application functioning deviates from the test cases written | Srikanth Reddy Narra | 15 | 2022-10-22 | 2022-11-06
1 | 8 | Deployment | The developed application is deployed by project team and is made ready to use by users | Project Team | 30 | 2022-11-06 | 2022-12-06
2 | 8.1 | Go-Live | The system is set to use in real time by users for checking availibility of pilots and schedules | Project Team | 30 | 2022-11-06 | 2022-12-06
1 | 9 | Maintenace | Post deployment issues, if customer identifies a bug or any missed feature in application | Project Team | TBD | TBD | TBD
2 | 9.1 | Identify the change | The new change request will be created by Husky Air with the missed feature as it is in scope | Husky Air | TBD | TBD | TBD
2 | 9.2 | Develop the change required | Development team will identify and gives fix for the required feature | Tianyu Nan | TBD | TBD | TBD
3 | 9.3 | Testing | The new test cases are created and the test results are documented for the test cases by testing team | Srikanth Reddy Narra | TBD | TBD | TBD
2 | 9.4 | Pilot program | A copy of original application is created in Quality environment and tested for originality by project team | Project Team | TBD | TBD | TBD
2 | 9.5 | Pre production backup | The backup of the data base and application code in live system is taken to use, in case of any system crash to re-deploy the backup code | Tianyu Nan | TBD | TBD | TBD
2 | 9.6 | Go-live | The change request will be moved into live system | Tianyu Nan | TBD | TBD | TBD
To be decided
Note:The duration of work on each day is 8 Hours and organization works from Monday through friday.

## RTM
Requirements Traceability Matrix
Project Name: Huskey Air Database Management
S.No | Phase | Person Responsible/ Requestor | Busienss Justification | WBS Task | WBS Strategy | Status
1 | Analysis | Nitish Katkoori | The project requirements and features are completely accessed and documented | 1,1.1,1.2,1.3,1.3.1,1.3.2,1.3.3,1.3.4 | The analysis of functional and technical requirements of the system are concluded | Pending
2 | Application Designing | Project Team | All the requirements for software and hardware have analyzed | 2.1 | The prototype testing is performed | Pending
3 | Webpage Design | Tianyu Nan | Frontend team write HTML code for webpage design | 3.1,3.1.1,3.1.2,3.2,3.2.1,3.2.2,3.3,3.3.1 | The froentend application look an dfeel is accessed | Pending
4 | Backend Code Development | Tianyu Nan | The required software or application code is developed after the requirements are finalized | 4.1,4.2,4.2.1,4.2.2,4.2.3,4.2.4 | Application code testing is done | Pending
5 | System Interfacing | Tianyu Nan | The technical team combined the frontend page with the backend code | 5.1,5.2 | Frontend and backend integration tests are performed upon completion of integration | Pending
6 | Data maintenance and migration | Tianyu Nan | The actual business data from the spreadsheet is maintained into new system and transactional data for the application is saved | 6.1,6.2 | The migrated data in the database is checked aganist the documented data by sampling procedure | Pending
7 | Quality Analysis/ Testing | Srikanth Reddy Narra | The applicataion should be tested for various cases and test results needs to be documented | 7.1,7.2,7.3 | The testing is done for quality check and the results are documented for process improvements | Pending
8 | Deployment | Project Team | The test results are sent for business approval, once the approval is received then the system is ready for deplolyment | 8.1 | Application is deployed for users with proper training to users | Pending
9 | Maintenace | Project Team | Process bugs in the application are identified, fixed, tested and deployed | 9.1,9.2,9.3,9.4,9.5,9.6 | Bugs are fixed and the new changes are deployed into live system | Pending

## Sheet1
1. BASIC RISK INFORMATION |  |  |  |  | 2. RISK ASSESSMENT INFORMATION |  |  |  |  | 3. RISK RESPONSE INFORMATION
Risk Number | Risk Description / Risk Event Statement | Responsible | Date Reported day-month-year | Last Update day-month-year | Impact H / M / L | Impact Description | Probability H / M / L | Timeline N/M/F | Status of Response N / P / PE / EE | Completed Actions | Planned Future Actions | Risk Status Open / Closed / Moved to Issue
R 1 | System conversion | Project Team | 2022-05-16 | 2022-07-04 | M | Migration of system from spreadsheet to online will not be smooth and requires some time for the developers to analyze | M | N | EE | 05/16/2022: Proper analysis on the spreadsheet system by development team. 06/06/2022:Discussed the requiremnets with the customer before finalization. 07/04/2022: Customer confirmed the requirements are as expected | NA | Closed
R 2 | System failure | Tianyu Nan | 2022-05-09 | 2022-07-15 | H | The system may have risk of failure due to internet issues. So, down time may be issued for the customers | L | M | EE | 05/09/2022: Discuss with the customer on how capable they are ready to invest on internet. 07/08/2022: Looked for another internet connection from a different internet service provider, and use it as a backup connection. 07/15/2022: The customer accepted the new internet service provider as a backup one. | NA | Open
R 3 | Data loss | Tianyu Nan | 2022-08-20 | 2022-09-02 | H | The customers may use multiple applications at the same time while filling his/her details for registration. The customer's passwords and ID may be compromised | M | F | PE | 08/20/2022: Discussion with customer on features of navigation between different applications. 08/29/2022: Customer requested to give an update on it in future. 09/02/2022: Customer confirmed on restricting the navigation between applications while usage | 09/08/2022: Write a code to restrict navigation between applications | Open
R 4 | Additional Infra- structure needs | Camille Wu | 2022-06-11 | 2022-07-24 | M | There might be a need for additional resource during the development. There may be extra hardware and software requirements during the project's development. | M | N | EE | 06/11/2022: letting the customer know about more efforts or people required for developing the web page. 07/10/2022: Customer acceptance to provide extra devices and software required for development and testing. 07/24/2022: Started procedure to onboard the new employee and set to work | NA | Closed
R 5 | Project Timeline Crunch | Camille Wu | 2022-08-03 | 2022-08-26 | M | The shortage of time may occur in any stage of project | H | N | PE | 08/03/2022: Discussing with customer on extending the work hours to meet the actual deliverables and timelines of the project. 08/26/2022: Customer accepted for providing extra budget. | 09/03/2022:Give a plan for re-budgeting due to extra working hours | Closed
R 6 | Team member Change | Camille Wu | 2022-05-20 | 2022-07-24 | L | People leave the organization may have direcr or indirect effect on budget and time | L | M | PE | 05/20/2022:Implementing employee commitement and relieving policies throughout the project. 05/24/2022: Taking employee undertaking to be in project until closure | 07/25/2022: Plan the preparation of updated training manuals, new resource training, and reverse knowledge transfer | Closed