## Title
Course
OM&IS 690
Project Name
Husky Air Database Management
Group Name
2
Submitted By
Nitish Katkoori (Z1942695)
Srikanth Reddy Narra (Z1947038)
Tianyu Nan (Z1831431)
Date
2022-07-17

## Work Breakdown Structure
WBS Level | WBS Code | WBS Name | WBS Description | Person Responsible | Duration (Days) | Start | End
1 | 1 | Analysis Phase | Analyses all the requirements for development and the project | Nitish Katkoori | 23 | 2022-05-14 | 2022-06-06
2 | 1.1 | Requirement Gathering and analysis | Project Manager to collect all the needed requirements from customer and Husky Air for development of the project | Nitish Katkoori | 1 | 2022-05-14 | 2022-05-15
2 | 1.2 | Stakeholder Interviews | Project manager schedules interview with stakeholder on clarifications required by the team | Nitish Katkoori | 2 | 2022-05-15 | 2022-05-17
2 | 1.3 | Create requirements document | Project manager collect all of the requirements and produce a document for requirements | Nitish Katkoori | 1 | 2022-05-19 | 2022-05-20
3 | 1.3.1 | Business Case | Produce the reason and primary goal for this project | Nitish Katkoori | 1 | 2022-05-20 | 2022-05-21
3 | 1.3.2 | Create project charter | Produce project charter document | Nitish Katkoori | 8 | 2022-05-29 | 2022-06-06
3 | 1.3.3 | Project Scope | Produce the needs and things that are required to be determined for this project | Nitish Katkoori | 1 | 2022-05-21 | 2022-05-22
2 | 1.4 | Project Schedule | Project manager creates tasks and assigning deadlines for development, testing and deployment of the project by considering the efforts required | Nitish Katkoori | 14 | 2022-05-22 | 2022-06-05
1 | 2 | Application Designing | Design the application for mobile devices and website | Project Team | 3 | 2022-06-06 | 2022-06-09
2 | 2.1 | Software and Hardware requirements | Project team analyses all the requirements for software and hardware | Project Team | 3 | 2022-06-06 | 2022-06-09
1 | 3 | Webpage Design | Frontend team write HTML code for webpage design | Tianyu Nan | 28 | 2022-06-09 | 2022-07-07
2 | 3.1 | Home page and login page for Website | Frontend development team creates high level design for website | Tianyu Nan | 2 | 2022-06-09 | 2022-06-11
3 | 3.1.1 | User Interface design for Mobile application | Frontend development team works on developing customer login screen to the mobile application | Tianyu Nan | 4 | 2022-06-11 | 2022-06-15
3 | 3.1.2 | User Interface design for Web application | The UI for customer login to the web based application is developed by frontend team | Tianyu Nan | 5 | 2022-06-15 | 2022-06-20
2 | 3.2 | User aggrement/ policy page | Design user aggrement or policy page for both Website and mobile application | Tianyu Nan | 1 | 2022-06-20 | 2022-06-21
3 | 3.2.1 | Agreement/ policy page design for Mobile application | Frontend team design a screen for agreement/ policies for mobile application based on page resolution upon login | Tianyu Nan | 1 | 2022-06-21 | 2022-06-22
3 | 3.2.2 | Agreement/ Policy page design for Web application | Frontend team design a screen for agreement/ policies for Web application based on page resolution | Tianyu Nan | 1 | 2022-06-22 | 2022-06-23
2 | 3.3 | Visual design for Website and mobile application | Frontend team develops design for website and mobile application with all dropdown actions | Tianyu Nan | 6 | 2022-06-23 | 2022-06-29
3 | 3.3.1 | Design page for Menu Dropdown | Frontend team devlop a menu drop down with Pilot availability,available aircrafts, customer request interface and scheduling interface | Tianyu Nan | 7 | 2022-06-29 | 2022-07-06
1 | 4 | Backend Code Development | Software development including coding, database implementation and security | Tianyu Nan | 60 | 2022-07-07 | 2022-09-05
2 | 4.1 | Login page credentials validation | Backend team develops a code to validate the login credentials with the data maintained in database | Tianyu Nan | 25 | 2022-07-08 | 2022-08-02
2 | 4.2 | Data base code for Menu Dropdown | Technical team write the backend code to show the following information in application drop downs | Tianyu Nan | 12 | 2022-08-03 | 2022-08-15
3 | 4.2.1 | Pilot availability | This code shows the pilots availability and is only accessible by Husky Air | Tianyu Nan | 8 | 2022-08-16 | 2022-08-24
3 | 4.2.2 | Available aircraft models | The customers can choose the available aircraft models based on their luggage | Tianyu Nan | 3 | 2022-08-25 | 2022-08-28
3 | 4.2.3 | Customer Requests interface | The customer requests for travel are put pool for approval by Husky air | Tianyu Nan | 3 | 2022-08-29 | 2022-09-01
3 | 4.2.4 | Scheduling interface | Pilot assignment based on customer requests of Husky air | Tianyu Nan | 4 | 2022-09-01 | 2022-09-05
1 | 5 | System Interfacing | Technical team to Integrate frontend page with backend logic | Tianyu Nan | 22 | 2022-09-06 | 2022-09-28
2 | 5.1 | Login page | Interface login page with backend logic credential validation code | Tianyu Nan | 5 | 2022-09-15 | 2022-09-20
2 | 5.2 | Menu Dropdown | Interface Menu dropdow page with corresponding backend logic | Tianyu Nan | 8 | 2022-09-20 | 2022-09-28
1 | 6 | Data maintenance and migration | Technical team updates the previous data of Husky air and the new transactional data to uskay air Database | Tianyu Nan | 13 | 2022-10-02 | 2022-10-15
2 | 6.1 | Data Migration | Technical team transports all the data from the pervious spreadsheet to new system database | Tianyu Nan | 9 | 2022-10-02 | 2022-10-11
2 | 6.2 | Store login details for patients and pilots | Store all the web/ application login and passwords details of pilots and patients to only allow access for registered users | Tianyu Nan | 2 | 2022-10-11 | 2022-10-13
1 | 7 | Quality Analysis/ Testing | Testing team prepare test cases and the results are documented | Srikanth Reddy Narra | 22 | 2022-10-15 | 2022-11-06
2 | 7.1 | Create test cases | Create the possible test cases to find any deviations from the usual process of application | Srikanth Reddy Narra | 2 | 2022-10-15 | 2022-10-17
2 | 7.2 | Validate test cases | Test the application for originality by testing team | Srikanth Reddy Narra | 5 | 2022-10-17 | 2022-10-22
2 | 7.3 | Document results | Testing team to document the results obtained while testing and revert to development team, if application functioning deviates from the test cases written | Srikanth Reddy Narra | 15 | 2022-10-22 | 2022-11-06
1 | 8 | Deployment | The developed application is deployed by project team and is made ready to use by users | Project Team | 30 | 2022-11-06 | 2022-12-06
2 | 8.1 | Go-Live | The system is set to use in real time by users for checking availibility of pilots and schedules | Project Team | 30 | 2022-11-06 | 2022-12-06
1 | 9 | Maintenace | Post deployment issues, if customer identifies a bug or any missed feature in application | Project Team | TBD | TBD | TBD
2 | 9.1 | Identify the change | The new change request will be created by Husky Air with the missed feature as it is in scope | Husky Air | TBD | TBD | TBD
2 | 9.2 | Develop the change required | Development team will identify and gives fix for the required feature | Tianyu Nan | TBD | TBD | TBD
3 | 9.3 | Testing | The new test cases are created and the test results are documented for the test cases by testing team | Srikanth Reddy Narra | TBD | TBD | TBD
2 | 9.4 | Pilot program | A copy of original application is created in Quality environment and tested for originality by project team | Project Team | TBD | TBD | TBD
2 | 9.5 | Pre production backup | The backup of the data base and application code in live system is taken to use, in case of any system crash to re-deploy the backup code | Tianyu Nan | TBD | TBD | TBD
2 | 9.6 | Go-live | The change request will be moved into live system | Tianyu Nan | TBD | TBD | TBD
To be decided
Note:The duration of work on each day is 8 Hours and organization works from Monday through friday.

## RTM
Requirements Traceability Matrix
Project Name: Huskey Air Database Management
S.No | Phase | Person Responsible/ Requestor | Busienss Justification | WBS Task | WBS Strategy | Status
1 | Analysis | Nitish Katkoori | The project requirements and features are completely accessed and documented | 1,1.1,1.2,1.3,1.3.1,1.3.2,1.3.3,1.3.4 | The analysis of functional and technical requirements of the system are concluded | Pending
2 | Application Designing | Project Team | All the requirements for software and hardware have analyzed | 2.1 | The prototype testing is performed | Pending
3 | Webpage Design | Tianyu Nan | Frontend team write HTML code for webpage design | 3.1,3.1.1,3.1.2,3.2,3.2.1,3.2.2,3.3,3.3.1 | The froentend application look an dfeel is accessed | Pending
4 | Backend Code Development | Tianyu Nan | The required software or application code is developed after the requirements are finalized | 4.1,4.2,4.2.1,4.2.2,4.2.3,4.2.4 | Application code testing is done | Pending
5 | System Interfacing | Tianyu Nan | The technical team combined the frontend page with the backend code | 5.1,5.2 | Frontend and backend integration tests are performed upon completion of integration | Pending
6 | Data maintenance and migration | Tianyu Nan | The actual business data from the spreadsheet is maintained into new system and transactional data for the application is saved | 6.1,6.2 | The migrated data in the database is checked aganist the documented data by sampling procedure | Pending
7 | Quality Analysis/ Testing | Srikanth Reddy Narra | The applicataion should be tested for various cases and test results needs to be documented | 7.1,7.2,7.3 | The testing is done for quality check and the results are documented for process improvements | Pending
8 | Deployment | Project Team | The test results are sent for business approval, once the approval is received then the system is ready for deplolyment | 8.1 | Application is deployed for users with proper training to users | Pending
9 | Maintenace | Project Team | Process bugs in the application are identified, fixed, tested and deployed | 9.1,9.2,9.3,9.4,9.5,9.6 | Bugs are fixed and the new changes are deployed into live system | Pending